## RACI Matrix
RACI Matrix Template
| Agathe | JB Jail | JB Relave | Duncan | François | Frédéric Paillart | Willy Duquenoy
Definition des objectifs | R | R | R | R | R | C/A
Plannification du projet | R | R | R | R | R | I
Rédaction de la charte projet | R | I | I | I | I | A
Conception de l'infrastructure Kubernetes | I | R | I | R | R | C
Conception du générateur de honeypot | S | I | R | I | I | C
Conception des micros services | S | R | I | I | I | C
Configuration des environnements de développement | A | R | R | R | I | I
Développement du générateur de honeypot | S | I | R | I | I | I
Développement des micros-services en Rust | S | I | R | I | I | I
Intégration des honeypots avec Kubernetes | I | R | R | S | S | I
Compilation des honeypots avec Wasm | S | I | R | I | I | I
Mise en place de l'environnement de récupération et d'analyse des logs | R | R | I | I | S | C
Déploiement de l'infrastructure Kubernetes sécurisée | I | R | I | R | S | C/A
Exposition des honeypots sur internet | I | I | I | I | R | C/A | C/A
Mise en place de l'analyse des logs en temps réel | R | S | R | I | A | I
Plannificationdes tests | R | I | I | I | I | I
Tests des honeypots | I | I | R | I | I | I
Tests des vulnérabilités | I | I | R | I | I | I
Tests d'observabilité et d'analyse des logs | R | S | I | I | S | I
Récupération et analyse des logs | R | I | S | I | R | C
Réalisation de la documentation technique | R | I | I | I | I | I
Présentation du projet | R | R | R | R | R | C
Role
Project Activities (tasks)

## Instructions
Instructional Notes for the RACI Matrix:
The RACI Matrix is a powerful tool to assist in the identification of roles and assigning of cross-functional responsibilities to a project deliverable or activity. RACI represents: R - Responsibility, A - Accountable, C - Consulted, I - Informed, S - Support RACI Definitions: Responsibility = person or role responsible for ensuring that the item is completed Accountable = person or role responsible for actually doing or completing the item Consulted = person or role whose subject matter expertise is required in order to complete the item Informed = person or role that needs to be kept informed of the status of item completion Support = person who perform the tasks and report to R
Simply place an R, A, C, I, S or any appropriate combination in each of the applicable roles for each activity Each Activity should have at least one individual Accountable while there may be shared responsibilities depending on the activity.